Funding and Scaling Organics Courier

Funding and Scaling Organics Courier

SECTION 1: BYD KERRY - CASTLEISLAND DEALERSHIP

Dealer: BYD Kerry

Location: Castleisland, Co. Kerry

Contact: https://www.bydkerry.ie/en/contact-us

BYD ETP3 Electric Van (Best Fit for KOG):

- Price: EUR 14,950 (before SEAI grant)

- SEAI Grant (N1S): EUR 3,800

- Net Price: EUR 11,150

- Range: 280 km WLTP

- Payload: 1,000 kg

- Battery: 50.1 kWh

- Charging: 60 kW DC (30-80% in 30 mins)

- Warranty: 6 years / 150,000 km

- Why it wins: Cheapest electric van in Ireland, 1,000 kg payload, local Kerry dealer, 6-year warranty

BYD T3 Electric Van (Larger Option):

- Price: EUR 22,500 (before SEAI grant)

- SEAI Grant (N1L): EUR 7,600

- Net Price: EUR 14,900

- Range: 280 km WLTP

- Payload: 1,200 kg

- Battery: 50.1 kWh

- Charging: 60 kW DC

SECTION 2: PLAN A - WITHOUT/BEFORE VEHICLE GRANT

Strategy: Zero-capital launch using Cohort C (own-vehicle couriers) + rental e-bikes

Week 1-4: Pilot Launch (3 stores, 3 couriers)

- No fleet purchase. Use couriers with own cars/vans.

- Rent 2 pedal-assist cargo e-bikes at EUR 12/day each.

- Revenue: 5% store commission + EUR 6/9/14 distance-band fees.

- Cost: EUR 0 fleet capital. EUR 24/day bike rental.

- Break-even: 4 drops/day covers bike rental.

Week 5-8: Proof & Metrics

- Track: orders/day, delivery time, courier earnings, store satisfaction.

- Produce 1-page proof report for LEADER/LEO funding application.

- Target: 20 orders/day, 15-min drop time, EUR 15-20/hr courier pay.

Week 9-12: Scale to 10 Stores

- Add 7 more stores (Tralee/Killarney organic/halal/independent).

- Recruit 3 more Cohort C couriers.

- Revenue: EUR 2,000-3,000/month.

- Cost: EUR 720/month bike rental.

- Net: EUR 1,280-2,280/month.

SECTION 3: PLAN B - WITH VEHICLE GRANT

Strategy: SEAI grant + VRT relief + workplace charging for 3-van fleet

Vehicle Choice: BYD ETP3 (Castleisland)

- Purchase: EUR 14,950

- SEAI Grant: -EUR 3,800

- VRT Relief: -EUR 5,000

- Net: EUR 6,150 per van

- 3 vans: EUR 18,450 total

Workplace Charging Grant:

- 2 chargers x EUR 5,000 = EUR 10,000 grant

- Installation: EUR 3,000-5,000 (net EUR 0-2,000 after grant)

Total Fleet Cost: EUR 18,450 (vans) + EUR 2,000 (chargers) = EUR 20,450

Funding Sources:

- SEAI/ZEVI: EUR 11,400 (3 x EUR 3,800 grant + 3 x EUR 5,000 VRT)

- LEADER A&D: EUR 30,000 (feasibility study, not fleet)

- Kerry LEO: EUR 15,000 (feasibility, 50% match)

- Green Enterprise Pilot Scheme (GEPS): ERDF-funded, supports Kerry SMEs in low-carbon tech

SECTION 4: SUSTAINABLE LOGISTICS FUNDING ECOSYSTEM

EU Funding Programmes:

- Horizon Europe (Cluster 5): Zero-emission transport pilots. SMEs apply directly or as consortium partners.

- LIFE Programme: Up to 60% of project costs for clean transport, circular economy.

- European Regional Development Fund (ERDF): Managed via Kerry LEO for local business development.

- Just Transition Fund: Supports regions transitioning to low-carbon economies. Kerry qualifies.

Irish Funding Programmes:

- SEAI EV Grants: EUR 3,800 (N1S) / EUR 7,600 (N1L) per van.

- ZEVI Workplace Charging: Up to EUR 5,000 per charger.

- Green Enterprise Pilot Scheme (GEPS): ERDF-funded, supports Kerry SMEs in low-carbon tech.

- Energy & Environmental Aid (EI): Capital grant for decarbonisation projects.

- SBCI Green Transition Finance: EUR 500k-5M loans for sustainable SMEs.

Ecosystem Map:

1. Pilot Phase (Months 1-3): Cohort C couriers, no fleet capital. LEADER/LEO feasibility grant.

2. Scale Phase (Months 4-6): SEAI/ZEVI grants for 3 vans. GEPS for low-carbon validation.

3. Growth Phase (Months 7-12): Horizon Europe/LIFE for zero-emission logistics expansion.

4. Maturity Phase (Year 2): SBCI Green Transition Finance for fleet expansion to 22 stores.

SECTION 5: SOLAR RENEWABLE ENERGY PROSPECTS

SEAI Solar PV Grant (Business):

- Up to 60% of installation cost

- Maximum grant: EUR 90,000 for large businesses, EUR 30,000 for SMEs

- Covers: Panels, inverters, batteries, installation

- Payback: 4-7 years for commercial installations

KOG Solar Integration:

- Depot Roof (Tralee/Killarney): Install 10 kWp system (EUR 12,000-15,000)

- SEAI Grant: EUR 7,200-9,000 (60%)

- Net Cost: EUR 4,800-6,000

- Annual Savings: EUR 2,500-3,000 (electricity for vans + depot)

- Payback: 2-3 years

Vehicle-to-Grid (V2G) Future:

- BYD ETP3 supports bidirectional charging (future firmware)

- Sell excess solar back to grid during peak hours

- Additional revenue: EUR 500-1,000/year per van

SECTION 6: ORGANIC HORTICULTURE INCORPORATION

LEADER Theme 1: Economic Development & Job Creation

- Sub-theme: Rural Food Production, Agricultural Diversification

- Funding: Up to 90% for feasibility, 50% for capital

Organic Horticulture Grant Sources:

- Organic Farming Scheme (OFS): EUR 350-500/ha/year for certified organic land

- Targeted Agricultural Modernisation Scheme (TAMS): 60% grant on polytunnels, irrigation, cold storage

- LEADER Rural Food Production: Supports local food supply chains, farm-to-table initiatives

- Bord Bia Origin Green: Certification support for sustainable food producers

KOG Horticulture Integration:

- Partner with 3-5 local organic farms in Kerry

- Offer farm-to-door delivery service (same-day from harvest)

- Cold storage depot at Tralee/Killarney hubs

- Revenue share: 15% on farm produce, 5% on processed goods

- Job creation: 2-3 farm coordinators, 1 cold storage manager

SECTION 7: INTEGRATED ROADMAP

Phase 1 (Months 1-3): Pilot

- 3 stores, 3 Cohort C couriers, 2 rental e-bikes

- LEADER/LEO feasibility application

- Cost: EUR 0 fleet capital

Phase 2 (Months 4-6): Fleet & Solar

- 3 BYD ETP3 vans (SEAI + VRT = EUR 6,150 each)

- 10 kWp solar PV at Tralee depot (SEAI grant = EUR 7,200)

- Cold storage for organic produce

- Cost: EUR 25,000 (grants cover 60%)

Phase 3 (Months 7-12): Scale & Horticulture

- 10 stores, 6 vans, 10 couriers

- Partner with 5 organic farms

- Horizon Europe/LIFE application for zero-emission logistics

- Revenue: EUR 10,000-15,000/month

Phase 4 (Year 2): Ecosystem Maturity

- 22 stores, 11 vans, 20 couriers

- Full solar + V2G integration

- Organic horticulture supply chain established

- Revenue: EUR 30,000-50,000/month

SECTION 8: CONTACTS & LINKS

BYD Kerry: https://www.bydkerry.ie/en/contact-us

SEAI EV Grants: www.seai.ie/grants/electric-vehicle-grants

ZEVI Supports: www.zevi.ie/supports-schemes

Kerry LEO: 066 718 3522

NEWKD (LEADER): 066 718 0190

Organic Farming Scheme: www.gov.ie/organics

Bord Bia Origin Green: www.bordbia.ie/origingreen